## Single Issue Sheet
Issue
The text in the footer of chat box is not visible in dark mode
Suggestion: The header buttons (search, notifications, profile and mode switching) should be fixed on top when scrolled down. Currently, user has to scroll all the way up to use those functions
Inconsistent behaviour between List View and Grid view in Comfort tab as executive. List view says "No Rooms" but grid view just shows an empty page without any message.
Dark purple font in dark mode is not very reading-friendly
Search box is not clickable while in desktop mode but in portrait view(windowed mode or mobile view), the search is editable and appears different on almost all pages.
JSON Parse error comes up when user navigates to the building page for the second time from somewhere else.
User is unable to scroll down the list of rooms from temperature graph tooltip although there is a scrollbar present
Units are not present in "Total Estimated Annual Savings" under "AI Reports"
Value "17" for HVAC Status doesn't represent anything. Either the label should be "Total HVACs" or "HVACs Count" or soemthing
There is no way to read the full label text for tems in "Savings Potential by Category" under "AI Reports". Either the text should be scrolling or the widget should use the space on the right side
The color coding should be better for the numbers and should be distinguished from Alarm Severity or Device type.I had to pay attention to know that the alarms at number 2 and 4 are not "warnings" but "high" criticality alarms. The text of severity should be made a bit bigger or prominent. Because the number 2 is appearing yellow and my brain will be assosiating it with a warning instead of reading the fine print on the far right side about the actual severity
There is a lot of real-estate wasted under the alarms name and location. Maybe it can be designed a bit better to save space or to better utilize that space
The cursor should not appear as a clickable icon if the whole alarm item card is not clickable. Only the name and part is clickable so either show the mouse as clickable hand when hovering over the names and locations only or else make the whole card clickable
The user should be able to continue the conversation with AI Chatbot if he starts the conversation in the bottom right small window but then moves to the "AI Chatbot" page. Right now, whenever user does this, he loses all his chat history and it shows the option to only start a new conversation
If user goes from "Intellegence > AI Compliance" to "AI Operations > Maintainance" and then press back button, it will take user to the previous page but the same back button behaviour is not consistant throughout the website (e,g, From "Start/Stop" you can't come back to previous page).
The Side Menu icons are appearing too close to the labels and the alignment is also not consistent throughout the options
Vigneshwaran V
Issues
In Timewindow, History Tab, Grouping Interval selection is not updating.
In Timewindow, If we update the time using Realtime tab It's updating correctly in the Last updated column based on selection. But, while updating using History it shows '1 second' as last updated time.
In Alalrm Unassigned to Assigned, User Email Selection is not properly shown.
While assigned the user email, It shows null null.
Font Size is too small inside the Chart
Chart Header, Pleacemnet of chart headers and Font Styles consistency is missing
In Comfort Management, In List View If no rooms assigned "No rooms found" text there.While in the Grid view it's not there.
In Explore Menu, Building works on very 1st time. If you click back button and retrun to Explore Building again, it returns JSON PARSE Error
Font Size is too small in this value text
Legend text is not shown completely
In Settings Menu --> Permission Matrix Heading is too big compare to other sub menus in settings
In Settings Menu --> Workflow Management Heading is too big compare to other sub menus in settings
While adding New Role, Role names are not shown. It's showing only "Loading Roles..."
Athul Surendran
Shaharyar Haider
Visual missalignment in the Energy breakdown graph
History of data is not working, custom button is also not working
One of the cards is center aligned and one is right aligned, Where does this target and budget in Daily consumption vs target comes from?, Also here is an attached reference AI generated dashboard that might help in UI
No Rooms found in Monitor -> Comfort
Actual value (485 ppm) should be the main highlight like a subheading also the other information below the card such as Temperature and Humidity can be made better as shown in the attached generated dashboard using claude
Cannot see any red line as mentioned in the description of After Hour Compliance card
CO2 compliance for ALEMCO Head Office (DIC) seems misleading as it is based on 1 CO2 sensor only
Exception not posting in the center of the card
One Battery low alarm is Major one is minor fault why?
Too Hot and Too Cold graphs should say something like no rooms that are too hot or now room that are too cold instead of just saying no data available
It would be nice if all the values in the Room Temperature Regulation over hours of the day would be arranged in order of coldest to hottest rooms Also the Capatalization of letters in the heading is not consistent
Todays graph does not make sense also I cannot hover the points of todays graph The graph is of 2 days yet the date mentioned in the detail is for yesterday only
In "month" option this month graph is not showing at all also "PreviousWeek", "CurrentWeek", "PreviousMonth", "CurrentMonth" as no spaces in between the words
Difficult to differentiate the Red color for HVAC and yellow combined with purple colour for overlapping Lights and Presence
Inconsistent cards with and without symbols in all the devices
Shouldn’t the colour of Ambient vs Setpoint temperature be green with only a 0.4 difference?, to indicate it is close to setpoint?
Delta T could be named better to something like difference in Ambient and target temperature or a tool tip would be nice
Telemetry key (_DA_dailyFanspeedOffActive…....)showing also the High fan speed should be red and off should be grey
under assignment of alarms vvengadesh circle is not showing with initials
John Selastin
Ananth
Font inconsistency
broken chart and data isnt properly traversed(net usage is not divided rather reflected on everylevel)
Icons are not aligned
Dark mode button moved under profile despite there being enough space
Energy Breakdown graph text is too small
Sections intersect
Water graph has missing connections
CO2 graph has missing connections
One card is centered but the other is left aligned
Title card font, alignment, and size is inconsistent
Consumption Breakdown Energy: Which months are these? The current month just started but there’s data for week 2. Future data points should also not exist instead of being 0
Consumption Breakdown Water: Which months are these? Future data points should not exist instead of being 0
Unavailable data should be grey instead of red
Sort button becomes turns white after pressing it (only visible in dark mode)
Type LED but light not detected
Card says fault but no way to know what the fault is
Text is a little too small
Token has expired notification pops up and resets many times before finally displaying
Graph shows no data available for a second before actually loading the data
Default aggregation text says “Select a Time”
No target temperature shown in room level (Planning HOD)
Site, HVAC - Why is command 100 but feedback 10 Is there a large difference, or was the feedback not converted to % from volts
Site, HVAC - Picv command feedback have not been converted to % from volts
Site, HVAC - Raw key used when hovering over graph Change legend colours so off is grey
Site, Light - No spaces used in “6amTo6pm” and“6pmTo6am”
Site, Presence - No spaces used in “6amTo6pm” and“6pmTo6am”
Back button doesn’t go back to marina plaza, takes me to the same page
Unavailable devices should have grey text instead of red text
Marina Plaza levels are inverted?
Issues and Recommendations should be separated in some way
Yellow colour instead of green when compliant and stable
No legend for colours?
Roles never load
Jezreel Phillip Alvarez
Should only be "Floor" if there is 1 floor
When custom is selected for Grouping interval for time window aggregation the days, minutes, seconds cannot be selected.
Should be "Minute" if 1 minute
Year cannot be seen properly once long name is selected
Energy Breakdown for water is not connected for Marina
Assigning alarms does not appear in notification
Back Button should be in same format as other pages
There should be information, or legend on what the values mean for the values within the " ( ) ", and "3"
Unit of Temperature should be specified
Full name of category is not displayed
Critical Alarms is showing on notifications but not on Alarm Page
Assigning alarms to people with no surname shows last name as null
Comfort page should say that there is no information to be viewed on the page instead of blank page
Current status Font color should match based on the legend given
Afrin Fathima
change card name daily Active hours (6am to 6pm) - Business Hours and afterhours
Nihal Mascarenhas
Misalignment with other icons in the drawer
1. Overlapping of waves 2. Discontinuity of waves 3. Marina AES showing in whitespace category
Comfot management not rendering
Showing wrong error message. Temp. and Humi. sensor are present CO2 sensor is not present.
error message popping when opening - explore building
color code not matching the pop window color code Dangerous color code is the color code for severe
back bottom does not redirect to anywhere; if user starts on that page
Top 3 icons and bottom 4 icons are mis aligned
Ambiguity of this card. Should show the comparison and arrow could be facing wrong direction
Siji Wilson
Back button is not working in AI report
AI Report - Temperature Statistics card Text alignment is not correct
Space after Issues and recommendation card